HOUZEIFY

Master Product, UX, AI & SaaS Application Plan

Version 0.2  |  Working Draft for Review

Core product idea Houzeify is an AI-powered construction operating platform that connects homeowners, construction companies, builders, contractors, supervisors and site teams through one transparent digital construction record.

Prepared as a foundation for product discovery, UX design, engineering architecture and phased execution.

# Document Control

| Field | Value |
| --- | --- |
| Product | Houzeify |
| Document | Master Product, UX, AI & SaaS Application Plan |
| Version | 0.2 |
| Status | Working draft for review |
| Primary market assumption | India-first residential construction, with a structure that can expand to other markets and project types |
| Primary objective | Define a scalable product foundation before UI implementation and engineering |
| Important note | Requirements in this document combine confirmed ideas discussed so far with clearly labeled recommendations. Product decisions should be reviewed before implementation. |

## How to Use This Document

This is intended to be a living master document. Review it section by section. New ideas should be added without breaking the shared project model. Confirmed requirements, assumptions, recommended decisions and future opportunities should remain visibly separated.

## Working Status Labels

| Label | Meaning |
| --- | --- |
| Confirmed requirement | Directly established in the current product discussion. |
| Recommended | A proposed product or architecture decision intended to make the platform scalable and easier to use. |
| MVP candidate | Potentially required for the first usable product release, subject to scope and validation. |
| Future | Important long-term capability that should not block the first release. |
| Open decision | Needs a business, UX, technical or operational decision before implementation. |

# Contents

1. Executive Summary

2. Problem, Opportunity & Product Vision

3. Houzeify Product Model

4. User, Organization & Project Roles

5. Project Scenarios Houzeify Must Support

6. End-to-End Customer and Partner Journeys

7. Construction Work Library & Standardized Task Model

8. Task Lifecycle: Yesterday, Today, Tomorrow

9. Daily Progress, Evidence & Digital Construction Record

10. Communication: Chat, Voice Messages, Calls & Video

11. AI Construction Advisor

12. Construction Estimation, BOQ & Pricing Model

13. Marketplace & Partner Lead Unlock Model

14. Company / Developer SaaS Project Management

15. Homeowner Transparency Experience

16. Contractor, Supervisor & Worker Experiences

17. Permissions, Roles & Data Visibility

18. Core Product Modules

19. Data Model & Domain Architecture

20. Recommended Technology Architecture

21. Notifications, Automation & AI Events

22. Monetization & SaaS Model

23. Security, Privacy & Trust

24. MVP and Phased Product Roadmap

25. UX Principles & Design System Direction

26. Success Metrics & Product KPIs

27. Major Risks & Mitigations

28. Open Decisions for Review

29. Build Checklist / Next Steps

30. Detailed Screen Inventory

31. Functional Requirements & Acceptance Criteria

# 1. Executive Summary

Houzeify is envisioned as a connected construction platform for two major realities: homeowners who need construction help or visibility, and construction organizations that need a structured way to execute, document and communicate work.

The platform must support both marketplace-led and company-led construction. A homeowner can create a construction requirement and use the AI Construction Advisor to generate an estimate, publish the requirement and receive proposals from partners. A developer or construction company can instead subscribe to Houzeify, create an already-existing project such as a 170-villa development, add contractors and site teams, and give buyers access to a simplified customer view.

The platform becomes differentiated when construction work is modeled as structured data instead of free-form updates. Every project uses a standardized Construction Work Library containing stages, trades, work types, task templates, checklists, units, dependencies and evidence requirements. This creates one common language between AI estimation, task creation, daily progress, workforce tracking, customer transparency and project reporting.

North-star product statement Make construction visible and manageable from anywhere by connecting People + Work + Progress + Evidence + Communication + AI in one project record.

# 2. Problem, Opportunity & Product Vision

## 2.1 Problem statement

Homeowners often cannot be physically present on a construction site throughout the day. At the same time, construction companies and site teams need to coordinate many people, activities, materials, tasks and updates. Existing communication may be fragmented across calls, WhatsApp messages, spreadsheets, photos and informal conversations.

The result is a visibility and accountability gap: the homeowner wants to know what happened, the construction company wants reliable project records, the contractor needs clear assignments and the site team needs a fast way to report real work.

## 2.2 Opportunity

Houzeify can become the connection between the construction site and everyone who depends on the site. Instead of asking “What happened today?”, the product can produce a structured answer: who worked, what work happened, what was completed, what evidence exists, what issues occurred, what is planned next and how current progress compares with the plan.

## 2.3 Product vision

Construction should not stop being visible just because a homeowner is away from the site. Houzeify provides visibility without physical presence while giving construction teams one place to plan, execute, document and communicate the work.

## 2.4 Long-term positioning

Recommended positioning: “AI-powered construction operating platform” rather than “construction project management app.” The platform can eventually combine three businesses: an AI construction advisor, a construction marketplace and construction-management SaaS.

| Layer | Purpose | Primary users |
| --- | --- | --- |
| AI Construction Advisor | Estimate, interpret, summarize and assist with construction work. | Homeowner, contractor, project manager, site supervisor |
| Construction Marketplace | Connect homeowners and construction partners. | Homeowner, contractor, builder, construction company |
| Construction SaaS | Manage project execution, people, work and records. | Developer, construction company, contractor, supervisor, site team |
| Digital Construction Record | Maintain the long-term evidence and history of what happened. | All authorized project stakeholders |

# 3. Houzeify Product Model

The most important architecture decision is to model Houzeify around Projects and project membership rather than permanent user types. A person or company can participate in multiple projects with different roles.

PERSON / COMPANY ↓ ORGANIZATION / ACCOUNT ↓ PROJECT ↓ PROPERTY / UNIT / LOCATION ↓ STAGE → TRADE → WORK TYPE → TASK ↓ WORKFORCE → PROGRESS → EVIDENCE → RECORD

## 3.1 Two product states

| State | Meaning |
| --- | --- |
| Marketplace | A person/company is looking for construction work or looking for a partner. The relationship is not yet an active project. |
| Project | A construction engagement already exists. The focus becomes planning, execution, evidence, communication, reporting and customer visibility. |

Critical distinction Marketplace = Find / Win Work. Project = Execute / Track Work. The same contractor account can move from one state to the other without creating a second identity.

# 4. User, Organization & Project Roles

## 4.1 Primary user groups

| Role | Primary need | Typical access |
| --- | --- | --- |
| Homeowner / Buyer | Understand estimate, contractor selection or current project progress. | Own property/project customer view; communication with authorized team |
| Developer / Construction Company | Manage portfolios, projects, contractors, workforce, progress and customer transparency. | Full organization/project management |
| Builder / Main Contractor | Win projects or execute assigned project scope. | Marketplace + assigned project operations |
| Subcontractor / Trade Contractor | Receive assigned work, manage workers and submit progress. | Assigned project, trade scope and workforce |
| Project Manager | Coordinate the project and maintain overall execution. | Broad project management |
| Site Supervisor | Create/update tasks, capture evidence and coordinate site activity. | Day-to-day site operations |
| Site Worker | See assigned work and provide simple progress evidence. | Highly simplified task-based mobile access |
| Architect / Consultant | Review relevant project information and inspections. | Limited project/document access |

## 4.2 Roles are contextual

A contractor should not be hard-coded as “only a contractor.” The same account might discover a job in the marketplace, execute another project as a subcontractor, and manage a separate project as a main contractor. Permissions should therefore be attached to the person/company’s membership in a project or organization.

# 5. Project Scenarios Houzeify Must Support

## Scenario A — Homeowner looking for a contractor

Homeowner → AI Estimate → Requirement → Marketplace Post → Partner Unlock → Proposal → Selection → Project

This is the classic marketplace journey. Houzeify generates an initial construction estimate, packages the customer’s need into a structured requirement and allows relevant partners to discover the opportunity. A paid unlock can reveal additional information and enable the partner to prepare a proposal.

## Scenario B — Homeowner already hired a contractor

Existing construction → Company/Contractor creates Project → Invite Homeowner → Customer View → Daily Progress

The homeowner is not searching for work. Their main need is transparency. The project may already be months old. Houzeify must allow “Start Tracking Existing Project” and capture the current stage, baseline progress and people involved.

## Scenario C — Contractor searching for projects

Contractor → Partner Profile → Discover Opportunities → Unlock → Estimate / Proposal → Win

The contractor uses Houzeify as a business-development channel. They can discover opportunities by location, trade, project type and other criteria, then pay to unlock selected requirements.

## Scenario D — Contractor already hired by a developer

Developer → Project → Assign Trade Contractor → Assign Scope → Contractor Workspace → Workforce → Daily Progress

The contractor is not a lead-generation user for this project. They are an execution partner. Houzeify must support a large project hierarchy such as developer → 170-villa development → blocks/units → trades → tasks → workers.

## Scenario E — Developer manages many buyers

A single developer project may contain hundreds of units, each with a different homeowner. The developer sees the whole project portfolio, while each homeowner sees only the property or unit they are entitled to view.

# 6. End-to-End Customer and Partner Journeys

## 6.1 Homeowner marketplace journey

Create account and verify contact details.

Enter project type, location, built-up area and high-level requirements.

Use AI Construction Advisor to produce an indicative estimate.

Review assumptions, inclusions, exclusions and price freshness.

Convert estimate into a structured construction requirement.

Publish requirement to the marketplace.

Receive partner interest / proposals.

Compare partners, estimates, experience and proposal details.

Select a partner and convert opportunity into an active project.

Track project execution through the homeowner view.

## 6.2 Company/developer journey

Create organization and subscription.

Create project or import an existing project.

Define units/blocks/locations and project baseline.

Add contractors, supervisors and project members.

Assign scopes and standardized work categories.

Create task plans using the Construction Work Library.

Contractors/supervisors execute work and submit evidence.

Project team reviews progress, issues, workforce and deviations.

Invite homeowners/buyers to controlled project views.

## 6.3 Contractor journey

A contractor has two main modes. “Find Work” supports marketplace discovery, paid unlocks, estimates and proposals. “Deliver Work” supports assigned projects, tasks, workforce, progress, evidence and communication.

# 7. Construction Work Library & Standardized Task Model

The Construction Work Library is a foundational Houzeify capability. The goal is to make work selectable, measurable and understandable across projects. Contractors should choose standardized work rather than repeatedly typing descriptions.

## 7.1 Recommended hierarchy

PROJECT └── STAGE └── TRADE └── WORK TYPE └── TASK TEMPLATE ├── Checklist ├── Unit / Quantity ├── Skill / Workforce ├── Dependencies ├── Evidence requirements └── Completion rules

## 7.2 Initial residential construction stage library

### Pre-construction & Site Preparation

Survey, site clearing, site office, temporary utilities, setting out, excavation marking, soil testing, compaction, filling, leveling.

### Foundation

Excavation, PCC, footing reinforcement, footing formwork, footing concrete, pedestal, foundation wall, anti-termite, waterproofing, backfilling.

### Plinth

Plinth masonry, plinth beam, DPC, filling, compaction, soling, PCC, plinth waterproofing.

### RCC Structural Work

Column reinforcement, column shuttering, column casting, beam reinforcement, beam shuttering, beam casting, slab reinforcement, slab shuttering, slab casting, staircase reinforcement/shuttering/casting, curing, de-shuttering.

### Masonry & Block Work

Brick masonry, AAC blocks, concrete blocks, internal partitions, external walls, openings, lintels, parapets and wall repairs.

### Plastering

Internal plaster, external plaster, ceiling plaster, surface leveling, corner finishing, waterproof plaster where applicable.

### Waterproofing

Foundation, basement, toilet, balcony, terrace, podium, water tanks, retaining walls.

### Plumbing

Water supply, drainage, soil/waste pipes, toilet plumbing, kitchen plumbing, tank connections, pumps, rainwater, sewer, fixture installation, testing.

### Electrical

Conduit, slab conduit, wall conduit, wiring, switch boxes, sockets, lighting points, DB, main cable, earthing, meter connection, testing, solar electrical work.

### HVAC / Mechanical

AC piping, drain lines, refrigerant lines, indoor/outdoor unit work, ducting, ventilation, exhaust, testing/commissioning.

### Flooring & Tiling

Floor tiles, wall tiles, bathroom tiling, kitchen backsplash, granite, marble, stone, skirting, staircase finishes, outdoor pavers, grouting, polishing.

### Doors & Windows

Door frames, shutters, windows, aluminium, uPVC, glass, sliding systems, hardware, locks, handles.

### Carpentry & Joinery

Doors, wardrobes, kitchen cabinets, TV units, storage, partitions, furniture installation, hardware.

### False Ceiling & Interiors

Gypsum ceiling, POP, grid ceiling, cove lighting, framing, wall paneling, gypsum partitions, acoustic panels.

### Painting

Surface preparation, putty, primer, interior paint, exterior weather coat, metal paint, wood polish, texture, touch-up.

### Kitchen

Countertops, granite, modular cabinets, sink, plumbing, electrical points, backsplash, appliances.

### Bathroom & Sanitary

Waterproofing, tiling, WC, basin, shower, faucets, accessories, mirror, exhaust, testing.

### External Development

Roads, pavers, drainage, landscaping, compound wall, gate, parking, utilities, sewer, external water, external electrical, landscape lighting, security.

### Testing & Handover

Electrical testing, plumbing testing, waterproofing tests, inspections, snagging, defect rectification, cleaning, documentation, final handover.

## 7.3 Trade / workforce library

| Trade group | Example roles |
| --- | --- |
| Civil / RCC | Mason, helper, RCC worker, bar bender, shuttering carpenter, concrete worker, tile mason |
| Electrical | Electrician, electrical helper, cable technician, solar technician |
| Plumbing | Plumber, plumbing helper, sanitary installer |
| Finishing | Painter, gypsum installer, POP worker, marble worker, tile worker, carpenter |
| Specialized | Welder, fabricator, aluminium technician, glass installer, waterproofing technician, HVAC technician, landscaper |

# 8. Task Lifecycle: Yesterday, Today, Tomorrow

“Yesterday → Today → Tomorrow” should become a signature UX pattern for construction. It matches how site teams actually communicate and gives homeowners a simple narrative of what happened, what is happening and what comes next.

## 8.1 Task creation

| Field | Example |
| --- | --- |
| Project | Green Valley Villas |
| Property / Location | Villa 042, First Floor |
| Stage | RCC Structural Work |
| Trade | Reinforcement |
| Work Type | Column Reinforcement |
| Task template | Column Reinforcement - Standard |
| Quantity | 12 columns |
| Assigned contractor | ABC Civil Works |
| Supervisor | Suresh |
| Planned workforce | 6 |
| Start / due date | 26 Sep - 27 Sep |
| Evidence | Before, during, completed |

## 8.2 Standard task lifecycle

Draft → Assigned → Accepted → Ready → In Progress → Submitted → Review → Approved → Completed

A task may also move into Blocked, Delayed, Reopened or Cancelled states. State transitions should be logged so the project record shows when and why work changed status.

## 8.3 Task template concept

A task template should contain a default checklist, suggested evidence, expected trade/skill, default unit, typical dependency and optional quality criteria. A project user can override project-specific values without changing the master template.

# 9. Daily Progress, Evidence & Digital Construction Record

Daily Progress is the bridge between on-site work and the digital project record. It should be optimized for quick mobile entry, especially for supervisors and contractors.

## 9.1 Daily progress record

| Field | Purpose |
| --- | --- |
| Project / Property / Location | Precisely connect the update to the right place. |
| Date and time | Establish a chronological record. |
| Trade and work type | Keep reporting structured. |
| Workers present | Capture workforce deployment. |
| Work planned | Compare intention with execution. |
| Work completed | Capture measurable output. |
| Progress % | Simple human-readable progress indicator, not the only metric. |
| Photos / videos | Visual evidence. |
| Voice note | Fast contextual explanation from the site. |
| Issue / blocker | Capture exceptions and reasons. |
| Next-day plan | Create forward visibility. |

## 9.2 Example daily record

Project: Green Valley Villas Unit: Villa 042 Trade: Electrical Date: 25 Sep Workers: 8 Work completed: Electrical conduit installation Progress: 65% → 78% Evidence: 12 photos + 1 video Issue: Material shortage Tomorrow: Switch box installation

## 9.3 Digital Construction Record

Every task and progress event should contribute to a permanent project history. Over time this record becomes the source for customer updates, reports, disputes, handover documentation, analytics and AI assistance.

# 10. Communication: Chat, Voice Messages, Calls & Video

Houzeify should reduce the need to move construction conversations into unstructured external messaging. Communication should remain connected to projects, tasks, issues and people where practical.

| Channel | Best use | Recommended behavior |
| --- | --- | --- |
| Project chat | General coordination across a project. | Persistent history, participants, mentions, files. |
| Task chat | Conversation about one activity. | Messages stay attached to the task record. |
| Direct message | Person-to-person coordination. | Permission-aware and project contextual. |
| Voice message | Fast site reporting / clarification. | Store audio, transcript when available, optionally create structured actions. |
| Voice call | Synchronous discussion. | In-app WebRTC/managed voice or phone handoff; retain call event and optional summary. |
| Video call | Inspections, remote walkthroughs. | Useful for manager/homeowner review; avoid making it a mandatory workflow. |

## 10.1 Voice-to-work workflow

Supervisor speaks → Transcription → AI intent extraction → Draft task/progress/issue → User confirms → Structured record

Example: “Today six masons worked on Villa 21 and completed the internal wall. Tomorrow start the first-floor plaster.” The AI could draft a daily progress entry plus the next-day task, but the user should remain in control of confirming the record.

## 10.2 Local-language opportunity

For an India-first product, multilingual voice and message support can become a major usability advantage. Telugu, Hindi and English are useful initial language targets depending on the selected market. The design should support transcription, translation and simplified worker-facing instructions without forcing every site team member to use the same language.

# 11. AI Construction Advisor

The AI Construction Advisor should be a product capability available across the lifecycle, not just a chatbot. AI should use the structured project data to generate useful outputs while showing assumptions and giving users control over changes.

| AI capability | User | Primary output |
| --- | --- | --- |
| Estimate generation | Homeowner / Contractor | Cost estimate, assumptions, quantities, materials, labour, finishing |
| Requirement interpretation | Homeowner / Contractor | Structured scope from natural language, voice or documents |
| Task generation | Project Manager / Supervisor | Draft tasks based on project stage, trade and plan |
| Voice-to-progress | Supervisor / Worker | Structured daily progress draft |
| Voice-to-task | Contractor / Supervisor | Task draft from spoken instruction |
| Progress summarization | Company / Homeowner | Yesterday / Today / Tomorrow and weekly summary |
| Issue summarization | Project Team | Open blockers, owners, age and status |
| Planned vs actual | Company / Contractor | Variance explanation and attention areas |
| Document understanding | Project Team | Extract relevant project information from drawings/docs where feasible |
| Customer Q&A | Homeowner | Plain-language explanation based on authorized project records |

## 11.1 AI principles

AI should be grounded in project data, not free-form invention.

Every important estimate should expose assumptions, inclusions, exclusions and confidence/uncertainty.

AI-generated changes should be drafts until a user confirms them.

AI should preserve traceability to the source data used for summaries and calculations.

AI should not silently alter project records.

# 12. Construction Estimation, BOQ & Pricing Model

Houzeify should treat estimation as structured data that can later be compared against planned and actual execution. BOQ should always mean “Bill of Quantities” in user-facing language.

## 12.1 Homeowner estimate flow

Requirements → Project parameters → AI estimate → Materials → Labour → Finishing → Other costs → Assumptions → Review → Save

## 12.2 Contractor estimate flow

Customer requirement → Review scope → AI Construction Advisor → Partner estimate → Adjust quantities/rates → Add exclusions → Generate proposal → Share link

## 12.3 Price architecture

“Present-day prices” should not be hard-coded. Houzeify needs a pricing data layer with source, geography, effective date, item category, unit, rate, confidence and update history. Where reliable current market data is unavailable, the product should clearly label values as estimates or assumptions rather than presenting them as verified market facts.

| Pricing entity | Key fields |
| --- | --- |
| Material price | Material, specification, unit, geography, rate, source, effective date, validity window |
| Labour rate | Trade/skill, geography, unit/day, source, effective date |
| Finishing rate | Finish category, specification, unit, geography, rate, source |
| Estimate line | Quantity, unit, price basis, amount, assumption, confidence |
| BOQ line | Item code, description, unit, planned quantity, rate, amount, source |

# 13. Marketplace & Partner Lead Unlock Model

The marketplace connects homeowners with construction partners. The monetization hypothesis is that partners may pay to access detailed requirements and customer information.

## 13.1 Visibility model

| Information state | Partner can see |
| --- | --- |
| Public / preview | High-level project type, location at approved granularity, broad scope, estimate range or summary, posted date. |
| Unlocked | Full requirement, detailed scope, project details, approved customer contact information and eligible documents. |
| Proposal submitted | Proposal status, communication and next actions as permitted. |
| Project won | Full execution workspace for assigned scope. |

## 13.2 Paid unlock principles

Price should be visible before payment.

The partner should know what additional information unlock provides.

Prevent repeat charges for the same requirement when appropriate.

Maintain an unlock ledger for billing, support and dispute resolution.

Customer contact information should be protected until the marketplace rules permit disclosure.

# 14. Company / Developer SaaS Project Management

This is the enterprise-facing side of Houzeify. A construction company or developer can subscribe, create or import projects, add contractors, manage workforce and provide buyers with a controlled transparency layer.

## 14.1 170-villa project model

Developer Organization └── Green Valley Villas ├── Block / Phase │ ├── Villa 001 → Homeowner A │ ├── Villa 002 → Homeowner B │ └── ... ├── Contractors │ ├── Civil │ ├── Electrical │ ├── Plumbing │ └── Painting ├── Supervisors └── Workforce

## 14.2 Portfolio to unit visibility

| Level | What the user sees |
| --- | --- |
| Portfolio | All projects, subscription status, health summary and key alerts. |
| Project | Overall progress, units, contractors, workforce, issues, reports. |
| Block / Phase | Progress across a subset of units. |
| Villa / Unit | Stage and trade progress for one home. |
| Task | Specific work item, evidence, communication and completion history. |

# 15. Homeowner Transparency Experience

The homeowner should see a simplified, trustworthy representation of the project. The customer experience should not replicate the internal construction-management interface.

## 15.1 Homeowner home screen

My Home Overall Progress: 72% Current Stage: Electrical Today • 8 workers on site • Conduit installation completed • 12 photos • 1 video Issue • Window material delayed by 1 day Tomorrow • Switch box installation

## 15.2 Customer communication

Customers should be able to ask questions through text or voice and request a call. The primary communication destination should normally be the authorized project/company team rather than individual site laborers.

## 15.3 Customer trust features

Clear timestamps for updates.

Original evidence metadata where appropriate.

Status labels that distinguish planned, reported, reviewed and completed work.

A visible change history for important project records.

Clear explanation when AI-generated information is an estimate or summary rather than a verified measurement.

# 16. Contractor, Supervisor & Worker Experiences

## 16.1 Contractor workspace

| Area | Purpose |
| --- | --- |
| Opportunities | Discover marketplace work. |
| My Projects | See awarded/assigned projects. |
| My Scope | See assigned trade, locations and work packages. |
| Tasks | Manage today’s and upcoming tasks. |
| Workforce | Assign and record workers. |
| Progress | Submit daily progress and evidence. |
| Issues | Track blockers and resolutions. |
| AI Construction Advisor | Estimate, summarize and assist. |

## 16.2 Supervisor mobile

Today My Work 1. Column Reinforcement - Villa 042 2. Masonry - Villa 043 3. Material Unloading - Villa 044 Open task → Start → Capture photo/video → Voice update → Complete

## 16.3 Worker mobile

Workers should have the simplest interface in the system. Their experience should focus on today’s assigned work, safety/quality prompts where required, evidence capture and completion. Complex reporting remains with supervisors or contractors unless the worker is explicitly assigned that responsibility.

## 16.4 Worker Onboarding & Workforce Operations

Worker onboarding must be deliberately lightweight. The company, contractor or authorized supervisor should add the worker; the worker should not need to create a full organization or configure a complex account. A worker can be assigned to one or more projects and can move between contractor/project assignments without losing historical records.

### 16.4.1 Worker creation methods

### 16.4.2 Minimum worker profile

Required fields should be kept to the minimum needed for work assignment and safe communication: name, mobile number (where available), preferred language, trade/skill and current project assignment. Optional fields can include worker photo, emergency contact, worker ID, contractor organization and employment category.

### 16.4.3 Worker invitation and activation

The invite should explain the project, the contractor/company inviting the worker, what access will be available and the basic permissions. Activation uses OTP or another approved authentication method. Access is not granted to unrelated projects simply because the worker has been invited to one project.

### 16.4.4 Worker assignment model

| Assignment field | Example |
| --- | --- |
| Worker | Ramesh Kumar |
| Trade | Mason |
| Skill level | Skilled |
| Contractor | ABC Civil Works |
| Project | Green Valley Villas |
| Scope | Villa 042–060 / Masonry |
| Supervisor | Suresh |
| Start date | 26 Sep 2026 |
| End date | Optional |
| Permissions | Assigned work + evidence + messages |

### 16.4.5 Worker mobile screen set

| Screen | Primary purpose |
| --- | --- |
| Worker Home / Today | Shows today’s project, assigned tasks, attendance and urgent messages. |
| Task Detail | Shows location, trade, work type, instructions, checklist, quantity and required evidence. |
| Voice Instruction | Play supervisor/contractor voice instructions; show transcript/translation when available. |
| Capture Evidence | Photo, video and voice capture linked directly to the current task. |
| Submit Progress | Record completed quantity, status, notes and evidence with as little typing as possible. |
| Blocked / Report Issue | Select a standard reason or send a voice explanation when work cannot continue. |
| Messages | Communicate with authorized supervisors/contractors through text, voice and approved call actions. |
| Attendance | Show check-in/check-out status and project attendance history according to the project policy. |
| Profile & Language | View basic identity, assigned organization/project and preferred language. |

### 16.4.6 Worker task interaction

The default worker flow is: Receive Task → Open Task → Listen/Read Instruction → Start Work → Capture Photo/Video/Voice → Report Quantity or Status → Submit → Supervisor Review. Construction-specific quantities should be used where possible (for example 4/8 columns, 450/800 sq ft, 18/30 electrical points) instead of asking the worker to invent a progress percentage.

### 16.4.7 Supervisor-assisted updates

When a worker has no smartphone, the supervisor can submit an update on the worker’s behalf. The system should store both the work owner (worker/team) and the submission actor (supervisor) so attribution remains clear. Evidence captured by the supervisor should not be mislabeled as worker-captured evidence.

### 16.4.8 Worker reassignment and offboarding

A worker can be unassigned from a project without deleting historical work. The worker’s past attendance, task participation and evidence remain attached to the project record, while active access is removed or changed according to the new assignment. Reassignment must preserve audit history.

### 16.4.9 Worker communication boundaries

Workers should normally communicate with assigned supervisors and contractors. Homeowner contact should be controlled by project role and policy; workers should not automatically receive private homeowner phone numbers or unrestricted customer access.

### 16.4.10 Worker UX principles

Use large, high-confidence actions and minimize typing.

Prioritize today’s work over analytics and administrative navigation.

Make camera, voice and evidence capture one or two taps away.

Support local-language labels, voice instructions and translated summaries where feasible.

Keep critical field actions tolerant of weak or intermittent connectivity with visible sync status.

Do not expose project/customer information beyond the worker’s assignment scope.

| Method | When to use | Flow |
| --- | --- | --- |
| Manual add | Small teams or one-off hires | Add worker → name/mobile/trade/skill/language → send invite → worker accepts → supervisor/company confirms. |
| QR join | Fast site onboarding | Supervisor generates project QR → worker scans → mobile + OTP → confirm identity → request to join → supervisor approves. |
| Bulk import | Large projects/developers | Upload CSV/XLSX → validate duplicates → map fields → assign contractor/project/trade → send invitations in batch. |
| Supervisor-assisted | Worker has no smartphone or cannot self-register | Supervisor creates/updates the worker record and submits progress on the worker/team’s behalf; the record clearly identifies the actual actor and the submitting supervisor. |

# 17. Permissions, Roles & Data Visibility

Permissions should be project-aware and scope-aware. For large developer projects, a contractor may be allowed to update electrical work across 170 villas but should not automatically see private information belonging to every buyer.

| Role | Project view | Update progress | Workforce | Customer details | Billing / org admin |
| --- | --- | --- | --- | --- | --- |
| Homeowner | Own project/unit | Limited / no operational edits | No | Own details | No |
| Developer admin | All | Yes | Yes | Yes per policy | Yes |
| Project manager | Broad project | Yes | Yes | Controlled | Limited |
| Main contractor | Assigned projects/scope | Yes | Own workforce | Controlled | No |
| Subcontractor | Assigned scope | Yes | Own workforce | Minimal | No |
| Supervisor | Assigned site/scope | Yes | Site workforce | Minimal | No |
| Worker | Assigned tasks | Evidence/complete | No | No | No |
| Supervisor | Add Worker | Create worker manually, select trade/skill and send invite. |  |  |  |
| Supervisor | Worker Invite / QR Join | Worker accepts invitation or joins by QR + OTP. |  |  |  |
| Supervisor | Bulk Worker Import | Import and validate workers for large projects. |  |  |  |
| Worker | Voice Instruction | Listen to assignment/voice guidance and transcript/translation. |  |  |  |
| Worker | Submit Progress | Enter quantity/status and submit evidence with minimal typing. |  |  |  |
| Worker | Attendance | View check-in/out and attendance status according to project policy. |  |  |  |
| Worker | Profile & Language | View identity, assigned projects and language preferences. |  |  |  |
| Supervisor | Submit for Worker | Record a worker/team update when the worker has no suitable device. |  |  |  |

## 17.1 Permission dimensions

Use multiple dimensions together: organization membership, project membership, role, assigned scope, property/unit access, data sensitivity and action type. This prevents an overly broad “contractor permission” from exposing information that should remain restricted.

# 18. Core Product Modules

The module set should explicitly include **Workforce & Worker Operations** and **Billing & Entitlements** as first-class platform modules. Workforce is not merely a contact list; it governs worker identity, project assignment, attendance, task access, evidence attribution and communication permissions. Billing governs subscriptions, marketplace unlocks, AI credits, storage and add-ons.

| Module | Purpose |
| --- | --- |
| Identity & Access | Login, phone/email verification, organizations, role switching, invitations, permissions. |
| Organization Management | Company profile, subscription, members, teams, branches, settings. |
| Project Management | Project creation, project type, location, phases, units, baselines. |
| Construction Work Library | Stages, trades, work types, task templates, checklists, dependencies. |
| Task Management | Assignment, status, priority, dates, quantities, checklists, evidence. |
| Workforce | Workers, trades, attendance/presence records, assigned work, contractor teams. |
| Daily Progress | Daily logs, planned vs actual, evidence, issues, next-day plan. |
| Media | Photo, video, audio, thumbnails, metadata, storage and access. |
| Communication | Chat, voice messages, calls, video, project/task conversations. |
| Marketplace | Requirements, opportunity discovery, unlocks, proposals, partner profiles. |
| Estimation / BOQ | AI estimates, price data, line items, quantities, revisions, BOQ and proposal outputs. |
| Documents | Plans, approvals, contracts, reports, handover documentation. |
| Customer Transparency | Homeowner project dashboard, timeline, evidence and questions. |
| AI | Advisor, summaries, extraction, task drafting, issue intelligence. |
| Notifications | Push, in-app, email/SMS where required, digests and alerts. |
| Billing | Subscriptions, partner unlock payments, invoices, usage and entitlements. |
| Admin | Moderation, pricing data administration, templates, support, audit and system controls. |
| Reporting | Operational reports, weekly reports, project summaries, exports. |

# 19. Data Model & Domain Architecture

The data model should preserve relationships among organizations, projects, locations, work, people and evidence. A relational database is recommended because construction data has many strong relationships and traceability requirements.

## 19.1 Core entities

Worker-specific entities should include WorkerProfile, WorkforceAssignment, AttendanceRecord, Skill/TradeProfile, Invitation, Device/Activation and WorkerSubmissionActor metadata. Billing entities should include Subscription, Plan, Entitlement, AddOn, CreditWallet, CreditTransaction, UnlockTransaction, Invoice and PaymentEvent.

| Entity | Examples / key relationships |
| --- | --- |
| User | Person, identity, preferences, language, contact methods. |
| Organization | Developer, construction company, contractor company. |
| Membership | User <-> organization role. |
| Project | Construction project, owner organization, project type, baseline. |
| Property / Unit | House, villa, apartment, block location. |
| Project Membership | User/company <-> project role and scope. |
| Stage | Foundation, RCC, masonry, finishing, etc. |
| Trade | Civil, electrical, plumbing, painting, etc. |
| Work Type | Standardized construction activity. |
| Task Template | Checklist, units, dependencies, evidence rules. |
| Task | Project-specific work item. |
| Worker | Person assigned to construction execution. |
| Daily Progress | Date-based work outcome. |
| Evidence | Photo, video, audio, document, timestamp, source. |
| Issue | Blocker, owner, severity, status, resolution. |
| Estimate | Versioned estimate with assumptions and sources. |
| BOQ | Structured Bill of Quantities. |
| Requirement | Marketplace project need. |
| Proposal | Partner response to a requirement. |
| Unlock Transaction | Partner payment for requirement access. |
| Communication Event | Message, voice note, call, call summary. |
| Notification | Event delivered to a user. |
| Subscription | Organization plan and entitlements. |

## 19.2 Event-oriented recordkeeping

Important changes should produce auditable events. Examples include task assigned, task started, evidence uploaded, issue created, issue resolved, estimate revised, customer invited, partner unlocked requirement and project status changed.

# 20. Recommended Technology Architecture

The recommended stack prioritizes a shared TypeScript ecosystem, mobile field efficiency, strong relational data and scalable media/AI services. The exact vendor versions should be revalidated at implementation start.

| Layer | Recommended technology | Reason |
| --- | --- | --- |
| Web SaaS | Next.js + React + TypeScript | Complex dashboards, project workspaces, admin and customer web experiences. |
| Mobile | React Native + Expo + TypeScript | Single iOS/Android codebase with camera, microphone and device integrations. |
| Backend | NestJS + TypeScript | Modular domain architecture suitable for a large SaaS backend. |
| Database | PostgreSQL + PostGIS | Relational construction model plus location-aware capabilities. |
| Auth | Supabase Auth initially or equivalent identity provider | Phone/email authentication and faster MVP implementation. |
| Realtime | Supabase Realtime initially or WebSocket layer | Live updates, chat and presence. |
| Media storage | Amazon S3 | Scalable storage for photos, videos, voice and documents. |
| Queue/cache | Redis | Background processing, caching and rate limiting. |
| AI | OpenAI API + Houzeify AI orchestration layer | Estimation assistance, transcription, extraction, summaries and assistant capabilities. |
| Realtime voice/video | LiveKit / WebRTC | Managed realtime communication. |
| Telephony | India-focused programmable voice provider such as Exotel | Phone calls, masking and call workflows where required. |
| Notifications | FCM + APNs | Mobile push notifications. |
| Payments | Razorpay initially | India-friendly subscriptions and marketplace payments. |
| Infrastructure | AWS with portable architecture | Long-term control and scalability. |
| Observability | Sentry + OpenTelemetry | Error monitoring and operational visibility. |

## 20.1 Architectural style

Recommended starting architecture Begin with a modular monolith, not microservices. Keep domain boundaries clean so high-load or specialized capabilities can be extracted later. This reduces early operational complexity while preserving a path to scale.

Web (Next.js) + Mobile (React Native) ↓ NestJS API + WebSockets ↓ Postgres/PostGIS + Redis + Object Storage ↓ AI / Media / Communication Services

# 21. Notifications, Automation & AI Events

Houzeify should be event-driven at the product level even if the first backend remains a modular monolith. Users should be notified when something requires attention, not for every minor event.

| Event | Potential notification |
| --- | --- |
| Task assigned | New task assigned to you. |
| Task overdue | Task due date has passed. |
| Progress submitted | Daily progress is ready for review. |
| Issue created | Issue needs attention. |
| Issue resolved | Issue resolution submitted. |
| Homeowner update | Your construction project has a new update. |
| Partner unlock | Requirement has been unlocked successfully. |
| Proposal received | A new proposal is available. |
| Estimate updated | A revised estimate is ready to review. |
| AI draft ready | AI created a draft progress/task/summary from your voice note. |

## 21.1 Notification channels

Use in-app and push notifications as primary channels. Email/SMS/WhatsApp integrations can be considered selectively for critical customer events, invitations, authentication and business notifications. Avoid notification overload.

# 22. Monetization & SaaS Model

## 22.1 Marketplace monetization

Partners can pay to unlock customer requirements. The unlock transaction is an explicit monetization event and should be tied to a clear value proposition: what information becomes available and what action the partner can take next.

## 22.2 SaaS monetization

Construction companies/developers can subscribe based on project count, units, active members, storage, advanced reporting, AI usage or a combination of these. A future enterprise tier can add organization-level controls, SSO, audit, advanced analytics and integrations.

## 22.4 Proposed Pricing Tables

The prices below are proposed starting hypotheses for product and business-model validation. They should not be treated as final market prices until Houzeify validates customer willingness to pay, AI/media infrastructure costs, project scale, lead conversion and competitive benchmarks. Pricing should also be region-aware if Houzeify expands beyond India.

### 22.4.1 Homeowner pricing

| Plan | Indicative price | Best for | Included capabilities |
| --- | --- | --- | --- |
| Free | ₹0 | Homeowners viewing or exploring | Project access, progress, timeline, photos/videos, basic messaging and limited AI access. |
| AI Estimate | ₹299 / estimate | Homeowners planning construction | AI Construction Advisor estimate, material/labour/finishing breakdown, assumptions and estimate review. |
| AI Plus | ₹799 / month | Active planning | Multiple estimates, revisions, BOQ support, material/labour analysis and increased AI usage. |
| AI Pro | ₹1,499 / month | Detailed planning | Advanced AI estimate workflows, document analysis, estimate comparison and expanded AI assistance. |

### 22.4.2 Contractor / partner pricing

| Plan | Indicative price | Best for | Included capabilities |
| --- | --- | --- | --- |
| Partner Free | ₹0 | Contractors joining marketplace | Profile, verification, portfolio and limited opportunity discovery. |
| Partner Credits | From ₹500 | Contractors looking for work | Credits used to unlock selected homeowner requirements; exact unlock cost varies by opportunity policy. |
| Contractor Starter | ₹1,499 / month | Individual/small contractors | Up to 3 active projects, tasks, daily progress, evidence, workforce basics and basic reports. |
| Contractor Pro | ₹3,999 / month | Growing contractors | Up to 15 active projects, larger teams, AI Advisor, voice-to-task, advanced progress and reporting. |
| Contractor Business | ₹7,999 / month | Established contractors | Up to 50 active projects, workforce management, AI, customer communication and advanced reporting. |

### 22.4.3 Construction company / developer pricing

| Plan | Indicative price | Suitable for | Example scale / capabilities |
| --- | --- | --- | --- |
| Company Starter | ₹4,999 / month | Small construction companies | Up to 3 active projects; project setup, contractors, tasks, progress, workforce and customer access. |
| Company Growth | ₹14,999 / month | Growing companies | Up to 10 active projects; advanced project management, workforce, reports, AI and communications. |
| Company Scale | ₹29,999 / month | Large construction companies | Up to 25 active projects; portfolio management, advanced AI, analytics and customer portal. |
| Developer Pro | ₹49,999 / month | Developers / multi-project builders | Large projects and multi-unit developments; units/villas, contractor management, workforce, AI and portfolio analytics. |
| Enterprise | Custom | Large developers / enterprises | Custom projects, units, users, storage, security, integrations, support and contractual SLAs. |

### 22.4.4 Marketplace lead-unlock pricing

| Opportunity type | Indicative unlock range | Pricing principle |
| --- | --- | --- |
| Small | ₹99–₹299 | Repair/small renovation; lower lead value. |
| Medium | ₹299–₹799 | Typical individual house work. |
| Large | ₹799–₹1,999 | Full-house or larger construction scope. |
| Premium | ₹1,999–₹4,999 | Higher-value villa or specialist opportunity. |
| Developer opportunity | Custom / higher credits | Large multi-unit or bulk scope; may be negotiated or tiered. |

### 22.4.5 AI credit pricing

| AI credit pack | Indicative price |
| --- | --- |
| 50 credits | ₹199 |
| 150 credits | ₹499 |
| 500 credits | ₹1,499 |
| 1,500 credits | ₹3,999 |
| Enterprise AI | Custom |

### 22.4.6 Illustrative AI usage

| AI operation | Proposed credit usage |
| --- | --- |
| Detailed construction estimate | 5–10 |
| Estimate revision | 2–5 |
| Bill of Quantities generation/analysis | 5–10 |
| Document / plan analysis | 5–15 |
| Voice → Task | 1 |
| Voice → Daily Progress | 1 |
| AI Daily Report | 1–2 |
| AI Project Analysis | 2–5 |

## 22.5 Billing, Entitlements & Add-ons

| Capability | Proposed billing approach |
| --- | --- |
| Subscriptions | Monthly or annual; annual target may offer approximately two months free as an acquisition hypothesis. |
| Projects / units | Entitlement-based limits rather than unlimited access on every plan. |
| Team members | Base allowance plus additional member packs where needed. |
| AI usage | Included allowance plus optional credit packs / plan upgrades. |
| Media storage | Included storage by plan; additional storage as an add-on. |
| Marketplace unlocks | Credit-based or per-opportunity payment, with unlock ledger and refund/dispute policy. |
| Advanced modules | Optional paid add-ons such as Live Site, advanced analytics, white-label customer portal and integrations. |
| Enterprise | Custom contract with security, support, integration and volume terms. |

Pricing architecture should expose entitlements rather than hard-code plan names into feature logic. A plan should resolve to capabilities such as active project limit, unit limit, member limit, storage limit, AI allowance, marketplace access, report access and premium module access. This allows pricing to change without redesigning the product architecture.

| Potential plan concept | Target user | Possible capabilities |
| --- | --- | --- |
| Starter | Small contractor | Limited active projects, tasks, workforce, customer access. |
| Professional | Growing contractor/company | More projects, reporting, AI, media and team controls. |
| Business | Construction company | Portfolio, contractor management, customer transparency, advanced reporting. |
| Enterprise | Large developer | Multi-project portfolio, advanced permissions, SSO, audit, custom integrations. |

## 22.3 Avoid a single revenue assumption

Treat the marketplace unlock model and SaaS subscription model as separate revenue engines. The product should not depend on one model succeeding before the other can operate.

# 23. Security, Privacy & Trust

Construction projects may contain customer identity, property information, contracts, documents, photographs and location data. Security must therefore be designed into the foundation rather than added after launch.

Strong authentication and session management.

Role- and scope-based authorization on every sensitive API action.

Signed/private media URLs rather than public buckets for sensitive project evidence.

Encryption in transit and at rest.

Audit trail for important changes and customer-data access.

Explicit consent and appropriate notice for call recording, voice processing and other communication features.

Retention policies for photos, videos, voice notes and personal data.

Backups and disaster recovery testing.

AI data governance: define what project information can be sent to external AI services and how long it is retained.

## 23.1 Trust principle

Construction record integrity A progress record should clearly distinguish what was planned, what was reported by a person, what was reviewed/approved by another person, and what was generated or summarized by AI.

# 24. MVP and Phased Product Roadmap

The recommended roadmap deliberately builds the shared construction core first. Marketplace and advanced AI should be added on top of that foundation rather than creating separate data models.

| Phase | Primary outcome |
| --- | --- |
| Phase 0 — Product foundation | Confirm roles, project model, work library, permissions, core UX architecture, pricing assumptions and technical decisions. |
| Phase 1 — Project Tracking MVP | Organization, projects, units, work library, tasks, contractor/supervisor roles, daily progress, photos, basic customer view. |
| Phase 2 — Communication | Project/task chat, voice messages, transcription, calls, notifications, activity timeline. |
| Phase 3 — SaaS Operations | Subscriptions, contractor management, workforce, reports, documents, portfolio dashboard, existing-project onboarding. |
| Phase 4 — Marketplace | Homeowner requirements, partner discovery, paid unlocks, proposals, partner profiles, project conversion. |
| Phase 5 — AI Construction Advisor | Estimate generation, BOQ assistance, structured requirement generation, voice-to-task, progress summaries. |
| Phase 6 — Construction Intelligence | Planned vs actual, issue intelligence, project summaries, AI analytics, richer document intelligence. |

## 24.1 Recommended MVP boundary

Do not overbuild the first release The first usable release should prove that a real construction team can create a project, assign standardized work, capture daily progress with evidence, communicate, and give a homeowner a trustworthy project view. Advanced AI, marketplace scale and complex forecasting can follow once this core loop works.

## 24.2 Core MVP loop

Create Project → Add People → Select Work → Assign Task → Work On Site → Capture Evidence → Submit Progress → Review → Customer Sees Update

# 25. UX Principles & Design System Direction

Houzeify should feel like a modern construction SaaS product: professional, visual, structured, trustworthy and human. It should not feel like a generic enterprise ERP or a social-media feed.

| Principle | Application |
| --- | --- |
| Construction-first | Use real construction language and meaningful work structures. |
| Progress before administration | The project screen should quickly answer “what is happening?” |
| Mobile-first for the site | Fast capture, large touch targets, minimal typing. |
| Structured over free-form | Prefer selecting stage/trade/work type over blank text fields. |
| Evidence matters | Photos/videos/voice are first-class project records. |
| Human review of AI | AI suggests; people confirm important changes. |
| Role-based simplicity | A homeowner should not see the complexity a project manager needs. |
| Traceability | Every important status or record should show when/by whom it changed. |
| Progress narrative | Yesterday → Today → Tomorrow should be highly visible. |
| Scalable hierarchy | Design for one house and 170 villas using the same mental model. |

## 25.1 Suggested information architecture

HOMEOWNER My Home ¦ Progress ¦ Timeline ¦ Photos ¦ Live Site ¦ Documents ¦ Questions COMPANY Overview ¦ Projects ¦ Progress ¦ Tasks ¦ Issues ¦ Workforce ¦ Contractors ¦ Documents ¦ BOQ ¦ Customers ¦ Reports ¦ AI CONTRACTOR Home ¦ Opportunities ¦ My Projects ¦ Tasks ¦ Workforce ¦ Progress ¦ Issues ¦ Messages ¦ AI SUPERVISOR Today ¦ Tasks ¦ Progress ¦ Workforce ¦ Issues ¦ Messages

# 26. Success Metrics & Product KPIs

| Area | Example KPI |
| --- | --- |
| Activation | % of new organizations that create a project and invite at least one team member. |
| Construction usage | Daily active project users; projects with weekly progress updates. |
| Reporting quality | % of active tasks with structured evidence and complete status. |
| Customer transparency | % of active homeowner projects receiving regular updates. |
| Marketplace | Requirement-to-unlock rate; unlock-to-proposal rate; proposal-to-project conversion. |
| SaaS | Trial-to-paid conversion; active organizations; retention; expansion within organization. |
| AI usefulness | AI draft acceptance rate; edit rate; estimate regeneration rate; user satisfaction. |
| Operational efficiency | Time required to create a progress update; reduction in manual reporting effort. |

# 27. Major Risks & Mitigations

| Risk | Why it matters | Mitigation |
| --- | --- | --- |
| Too many modules too early | Product becomes confusing and expensive to build. | Build around the core project loop and role-specific experiences. |
| Poor site adoption | If supervisors/workers do not report, the digital record becomes incomplete. | Mobile-first UX, voice-first input, fast task templates, minimal typing. |
| Unreliable price data | AI estimates may lose trust if pricing is stale or poorly sourced. | Pricing source/effective-date metadata, assumptions and confidence. |
| AI hallucination | Incorrect project/estimate information can be harmful. | Ground AI in structured project data, expose sources/assumptions, require confirmation. |
| Privacy leakage | Large projects may include sensitive buyer data. | Scope-based access, private media, audit logs, controlled customer-data disclosure. |
| Marketplace abuse | Spam, fake leads or low-quality partner activity can reduce trust. | Verification, moderation, reputation signals and transaction rules. |
| Complex permissions | Developer projects have many organizations and scopes. | Design RBAC/ABAC model early and test with realistic 170-villa scenarios. |
| Media costs | Video and photos can become expensive at scale. | Compression, lifecycle policies, thumbnails, quotas and storage analytics. |

# 28. Open Decisions for Review

These items should remain visible until the product/business direction is confirmed.

Should homeowner requirements be visible publicly at a high level, or only to verified partners?

How much does a partner pay to unlock a requirement: fixed, category-based, location-based, estimated project value-based or dynamic?

What customer information is revealed before and after unlock?

Should partners be allowed to send multiple revised proposals?

What constitutes a “project” versus a “requirement” versus a “proposal” in billing and reporting?

Which current-price data sources will Houzeify use for materials, labour and finishing?

Will prices be managed centrally by Houzeify, imported from partners/suppliers, or both?

How should project progress percentages be calculated: manual, quantity-based, task-based, weighted stage-based or hybrid?

Should homeowner progress be delayed until a supervisor/company approves it?

Which evidence is mandatory for each task template?

Will call recording be available, and under what consent/retention policy?

Which languages should be supported at launch?

Will live site CCTV/time-lapse be part of the first SaaS tier or a future add-on?

How should worker attendance/presence be captured: self check-in, supervisor entry, device location, QR or other methods?

How much of the AI estimate can be used as a formal proposal or contractual document?

What subscription limits define Starter, Professional, Business and Enterprise?

What worker onboarding methods are required at launch: manual invite, QR join, bulk import and supervisor-assisted onboarding?

Which worker fields are required for compliance, assignment and reporting, and which should remain optional?

Which worker actions should be available offline and how should queued evidence be reconciled?

Will homeowner-to-worker communication ever be permitted directly, or should the company/supervisor remain the communication boundary?

# 29. Build Checklist / Next Steps

The recommended order is to lock the product model before building individual screens.

| Step | Outcome |
| --- | --- |
| Step 1 | Confirm product scope and project scenarios. |
| Step 2 | Lock Organization → Project → Property/Unit → Role/Scope architecture. |
| Step 3 | Define complete Construction Work Library: stages, trades, work types, task templates. |
| Step 4 | Define task status model, checklist model and evidence requirements. |
| Step 5 | Design role-based navigation for homeowner, company, contractor, supervisor and worker. |
| Step 6 | Define permission matrix and data-visibility rules. |
| Step 7 | Define daily progress model and Digital Construction Record. |
| Step 8 | Define communication architecture: chat, voice, calls, video and notifications. |
| Step 9 | Define AI Construction Advisor input/output contracts and human approval checkpoints. |
| Step 10 | Define estimation/BOQ schema and pricing source strategy. |
| Step 11 | Design company/developer SaaS onboarding and existing-project migration. |
| Step 12 | Design homeowner transparency flow. |
| Step 13 | Design marketplace discovery, paid unlock and proposal flows. |
| Step 14 | Create API/domain architecture and database schema. |
| Step 15 | Build MVP around the daily construction loop. |
| Step 16 | Pilot with one or more real project teams; observe adoption and reporting behavior. |
| Step 17 | Refine the Work Library, permissions, customer view and AI workflows based on real usage. |

# 30. Detailed Screen Inventory

The screen inventory translates the product model into a concrete UX scope. These are logical screens, not a final navigation design. Several can be implemented as tabs, drawers, sheets or nested views depending on device and role.

## 30.1 Shared / identity screens

| Role | Screen | Primary purpose |
| --- | --- | --- |
| All | Welcome / product entry | Choose how to use Houzeify or continue to an invitation. |
| All | Login / OTP | Phone/email authentication and verification. |
| All | Profile | Personal details, language, contact preferences. |
| All | Role / context switcher | Switch active organization or project context when authorized. |
| All | Notifications | View actionable project and account notifications. |
| All | Messages | Access project, task and direct communications. |

## 30.2 Homeowner screens

| Role | Screen | Primary purpose |
| --- | --- | --- |
| Homeowner | My Home / Home Dashboard | Overall progress, today, issues, next steps, recent evidence. |
| Homeowner | AI Construction Advisor | Create or refine an estimate and ask construction questions. |
| Homeowner | Estimate | View material, labour, finishing and other estimate sections. |
| Homeowner | Requirement Builder | Convert estimate and preferences into a structured requirement. |
| Homeowner | Requirement Preview | Review what partners can see before publishing. |
| Homeowner | Marketplace Responses | See partner interest and proposals. |
| Homeowner | Proposal Detail | Review contractor proposal and assumptions. |
| Homeowner | Project Timeline | See chronological project activity. |
| Homeowner | Progress by Stage | See progress across construction stages. |
| Homeowner | Daily Update | Read a simple previous/today/next-day update. |
| Homeowner | Photos / Videos | Browse project evidence with timestamps. |
| Homeowner | Issues | See issues appropriate for customer visibility. |
| Homeowner | Documents | Access documents shared with the customer. |
| Homeowner | Ask Project Team | Text or voice question and request a call. |

## 30.3 Company / developer screens

| Role | Screen | Primary purpose |
| --- | --- | --- |
| Company | Portfolio Dashboard | All projects, health indicators, progress and alerts. |
| Company | Project List | Search and filter projects. |
| Company | Create Project | Create new or existing construction project. |
| Company | Project Overview | Summary of project health, units, contractors and progress. |
| Company | Project Structure | Blocks, phases, villas/units and locations. |
| Company | Contractors | Onboard, assign and manage contractors. |
| Company | Project Team | Project managers, supervisors, consultants and buyers. |
| Company | Work Library | Manage/select stages, trades and work templates. |
| Company | Work Plan | Build/review planned work by stage, trade and location. |
| Company | Tasks | Monitor work across locations and teams. |
| Company | Daily Progress Review | Review submitted updates and evidence. |
| Company | Workforce | View workers and deployment by trade/project. |
| Company | Issues | Track open, blocked and resolved issues. |
| Company | Documents | Plans, approvals, contracts, reports and handover files. |
| Company | BOQ / Cost | Review quantities, rates, estimate versions and cost structures. |
| Company | Customers / Homeowners | Invite and manage buyer access. |
| Company | Reports | Project and portfolio reporting. |
| Company | AI Construction Advisor | Ask for summaries, comparisons, drafts and project intelligence. |

## 30.4 Contractor screens

| Role | Screen | Primary purpose |
| --- | --- | --- |
| Contractor | Partner Dashboard | Opportunities, active projects, tasks, issues and pending updates. |
| Contractor | Opportunities | Discover relevant marketplace requirements. |
| Contractor | Requirement Preview | Evaluate an opportunity before paying to unlock. |
| Contractor | Unlock Checkout | Pay and confirm access to the requirement. |
| Contractor | Unlocked Requirement | Review customer details, scope and allowed documents. |
| Contractor | Proposal Builder | Create an estimate/proposal using AI assistance. |
| Contractor | My Projects | Projects already awarded/assigned. |
| Contractor | My Scope | Trade, locations and work packages assigned by a company. |
| Contractor | Task Board | Assigned, active, blocked, submitted and completed work. |
| Contractor | Workforce | Manage own workers and assignments. |
| Contractor | Daily Progress | Submit progress and evidence. |
| Contractor | Issues | Raise, assign or resolve construction blockers. |
| Contractor | Messages / Calls | Communicate with project team and customers where authorized. |
| Contractor | AI Advisor | Estimate, interpret, summarize and draft updates. |

## 30.5 Supervisor / worker screens

| Role | Screen | Primary purpose |
| --- | --- | --- |
| Supervisor | Today | All work requiring attention today. |
| Supervisor | Task Detail | Checklist, assignment, quantity, evidence and communication. |
| Supervisor | Capture | Photo, video and voice capture from the site. |
| Supervisor | Daily Progress | Submit what happened today and tomorrow plan. |
| Supervisor | Workforce Today | Record or verify workers present and trade. |
| Supervisor | Issues | Create and update blockers. |
| Supervisor | Messages | Project and task communication. |
| Worker | My Work Today | Simple assigned task list. |
| Worker | Task Detail | See instructions and required evidence. |
| Worker | Capture Evidence | Take photo/video/voice update. |
| Worker | Complete Task | Confirm completion or report a blocker. |

## 30.6 Admin / platform screens

| Role | Screen | Primary purpose |
| --- | --- | --- |
| Admin | Organizations | Manage organization onboarding and account support. |
| Admin | Users & Verification | Identity/business verification and moderation. |
| Admin | Construction Work Library | Maintain master stages, trades, work types and templates. |
| Admin | Pricing Data | Manage/review price feeds, dates, sources and geography. |
| Admin | Marketplace Moderation | Review requirements, partner quality and complaints. |
| Admin | Transactions | Unlock payments, refunds, invoices and reconciliation. |
| Admin | Subscriptions | Plans, entitlements and account status. |
| Admin | AI Controls | Prompt/configuration versions, usage limits, safety and audit views. |
| Admin | Audit Log | Security and sensitive-action history. |

# 31. Functional Requirements & Acceptance Criteria

The following requirements translate the master plan into implementation-ready statements. They are product-level requirements; engineering tickets should be created from them only after the scope is reviewed.

| ID | Domain | Requirement | Acceptance signal |
| --- | --- | --- | --- |
| FR-001 | Identity | Users must be able to create and verify an account using an approved authentication method. | Verified user can enter and access only authorized resources. |
| FR-002 | Organizations | A company can create an organization and invite members. | Invited members can accept and receive an organization role. |
| FR-003 | Project context | A user can belong to multiple organizations/projects with different roles. | Active context determines permissions and navigation. |
| FR-004 | Project creation | An authorized user can create a new project or start tracking an existing project. | Both new and already-running projects use the same project engine. |
| FR-005 | Units | A project can contain properties/units, blocks and phases. | User can drill from project to unit/property where authorized. |
| FR-006 | Work library | A user can select stage, trade and work type from a standardized library. | Standard tasks do not require free-form work naming. |
| FR-007 | Task templates | The system can apply a task template with checklist, unit and evidence rules. | Template defaults populate the task and can be overridden within permissions. |
| FR-008 | Task assignment | Authorized users can assign tasks to people/companies with dates and scope. | Assignee sees the task in their work queue. |
| FR-009 | Task state | Tasks support lifecycle states including blocked, delayed and reopened. | Every state change is timestamped and attributed. |
| FR-010 | Daily progress | Authorized site users can submit progress against project/unit/task scope. | Submission stores date, work, workforce, progress, evidence and next-day plan. |
| FR-011 | Evidence | Users can attach photos, videos and audio to authorized records. | Evidence links to the relevant project/task/progress record. |
| FR-012 | Voice message | Users can send voice messages in authorized conversations. | Recipient can play audio and view transcript when available. |
| FR-013 | Voice-to-structure | AI can draft task, progress or issue records from voice. | No important AI-generated change becomes final without appropriate confirmation. |
| FR-014 | Project chat | Authorized project members can participate in project chat. | Messages are retained according to communication policy. |
| FR-015 | Task chat | A task can contain contextual communication. | Task conversation is visible only to authorized participants. |
| FR-016 | Calls | Users can initiate voice/video calls through supported mechanisms. | Call event metadata is recorded; recording is policy/consent controlled. |
| FR-017 | Homeowner view | A homeowner can see a simplified project progress experience. | Only customer-authorized project/unit data is shown. |
| FR-018 | Company portfolio | A company can view multiple projects in one portfolio. | Project summaries respect organization permissions. |
| FR-019 | Contractor scope | A contractor sees assigned project scopes unless broader permissions are granted. | Cross-project or cross-unit data is not exposed by default. |
| FR-020 | Workforce | Contractors/supervisors can record workers assigned/present for relevant work. | Workforce records can be tied to trade and date. |
| FR-021 | Marketplace requirement | A homeowner can create and publish a structured requirement. | Requirement has controlled visibility states. |
| FR-022 | Marketplace discovery | A partner can discover requirements using approved filters. | Discovery excludes requirements outside partner rules/service areas. |
| FR-023 | Paid unlock | A partner can pay to unlock a requirement. | Payment creates a transaction and changes access per policy. |
| FR-024 | Proposal | A partner can build and submit a proposal against an unlocked requirement. | Proposal includes scope, price/estimate, assumptions and exclusions. |
| FR-025 | Shareable proposal | A contractor can share a proposal through a secure link. | Recipient sees only fields intended for sharing. |
| FR-026 | Partner selection | A homeowner can select/appoint a partner. | Selection activates the project relationship. |
| FR-027 | AI estimate | Homeowner or contractor can generate an AI-assisted estimate. | Estimate shows line items, assumptions, current-price basis and revision history. |
| FR-028 | Price data | Pricing records store source, geography and effective date. | UI does not silently present stale data as live market truth. |
| FR-029 | BOQ | The system supports a structured Bill of Quantities. | BOQ lines can be versioned and linked to estimate/project scope. |
| FR-030 | Planned vs actual | Project users can compare planned work to reported progress. | Variance can be viewed where sufficient data exists. |
| FR-031 | Issues | Authorized users can create, assign, prioritize and resolve issues. | Issue lifecycle and supporting evidence are retained. |
| FR-032 | Documents | Authorized users can upload and view project documents. | Document permissions follow organization/project scope. |
| FR-033 | Notifications | The system sends actionable notifications for important events. | Users can manage non-critical preferences. |
| FR-034 | Audit trail | Important sensitive changes create audit events. | Audit entry includes actor, action, target and timestamp. |
| FR-035 | Subscriptions | Organizations can subscribe to a plan. | Features and usage limits are enforced through entitlements. |
| FR-036 | Admin library | Admins can maintain stages/trades/work templates. | Template changes are versioned so existing project records retain meaning. |
| FR-037 | Customer privacy | Customer details are protected in marketplace and project contexts. | Access is granted only according to configured policy. |
| FR-038 | AI traceability | AI outputs retain references to relevant project context where feasible. | Users can distinguish reported facts from AI summaries. |
| FR-039 | Media processing | Uploaded media can be compressed, thumbnailed and processed asynchronously. | Upload experience remains usable on typical mobile connections. |
| FR-040 | Offline tolerance | Critical site capture workflows should tolerate temporary network loss. | Queued evidence can sync after connectivity returns with visible sync status. |
| FR-041 | Worker onboarding | Authorized company/contractor/supervisor can add a worker and send an invitation. | Worker receives a scoped invite and can activate through OTP or approved method. |
| FR-042 | Worker QR join | A project can expose a controlled QR join flow. | A scanned worker can request project access; authorized staff must approve unless policy explicitly permits auto-join. |
| FR-043 | Bulk worker import | Authorized users can import workers from CSV/XLSX. | Importer validates required fields, detects duplicates and reports errors before activation. |
| FR-044 | Worker profile | Worker records store trade, skill, language and active project assignments. | Worker can be assigned to relevant scopes without exposing unrelated projects. |
| FR-045 | Worker task experience | A worker can view only assigned tasks and required instructions/evidence. | Worker home prioritizes today’s work and hides unrelated administrative modules. |
| FR-046 | Worker evidence | A worker can submit photo, video and voice evidence against an assigned task. | Evidence is attributed to the worker and linked to task/progress with timestamps. |
| FR-047 | Supervisor-assisted progress | A supervisor can submit a worker/team update when the worker cannot self-submit. | System records the worker/team as work owner and supervisor as submission actor. |
| FR-048 | Worker attendance | Authorized supervisors/contractors can record or verify workforce attendance. | Attendance is linked to project, date, worker and relevant assignment/policy. |
| FR-049 | Worker reassignment | Workers can be unassigned or reassigned without deleting project history. | Historical work remains attributable and active permissions change with assignments. |
| FR-050 | Worker communication | Workers can communicate with authorized supervisors/contractors using permitted channels. | Direct customer contact is restricted unless explicitly authorized. |
| FR-051 | Offline field capture | Worker/supervisor evidence capture supports temporary connectivity loss. | Queued records show sync status and are reconciled without duplicate submissions after reconnect. |
| FR-052 | Pricing entitlements | The system evaluates plan and add-on entitlements for projects, users, storage, AI and marketplace access. | Feature availability and limits are enforced centrally and can change without code changes to each feature. |
| FR-053 | Pricing transactions | Marketplace unlocks, subscriptions, AI credits and add-ons produce billing records. | Each transaction has amount, currency, tax fields where applicable, status, timestamp and reference. |
| FR-054 | Worker language | Worker preferred language is stored and used for supported UI/voice experiences. | Supported labels/instructions can render in the selected language while retaining a canonical project record language. |

## 31.1 Example acceptance scenario: daily progress

Given a supervisor is assigned to Villa 042 When the supervisor opens Today And selects Electrical -> Conduit Installation And records 8 workers And captures photos and a voice update And submits progress Then Houzeify stores the daily record And the project manager receives a review notification And the homeowner sees the customer-appropriate update after the configured publication rule is satisfied.

## 31.2 Example acceptance scenario: marketplace unlock

Given a verified electrical contractor is viewing a requirement preview When the contractor chooses Unlock And completes the payment Then the transaction is recorded And the requirement moves to the contractor's unlocked list And only permitted customer/scope information becomes visible.

## 31.3 Example acceptance scenario: company-managed construction

Given a developer manages 170 villas When the company creates a project And imports/adds 170 units And assigns electrical scope to a contractor Then the contractor sees only the assigned scope And each supervisor can submit daily work against the relevant units And each homeowner sees only their authorized unit/project view.

# Final Product Definition (Working)

Working one-line definition Houzeify is an AI-powered construction operating platform connecting homeowners, construction companies, builders, contractors, supervisors and site teams from estimate and requirement through execution, daily progress, communication and final handover.

## Core product loop

Estimate → Requirement → Connect → Plan → Assign → Execute → Capture → Review → Communicate → Understand → Handover

## Core product principle

One platform. Multiple stakeholders. One shared construction model. One digital construction record.

END OF WORKING DRAFT v0.2